## Read me
SWGCG 301 - Phase 2 work distribution
Deadline: Sat 5 Dec 2026 23:59 ¦ Discussion: Sun 6 Dec 2026 16:00 ¦ Proposal: Sat 28 Nov 2026 23:59
Team: Mohamed (leader, the only one who submits on Moodle), Nour, Rahma, Hesham
How to use
1. Go to the Tasks sheet. Only change the Status column (dropdown) and Notes. Do not edit Weight/Owner without telling the team.
2. Weight = effort points (1 trivial, 2 easy, 3 medium, 4 hard, 5 very hard). It is an estimate, not a grade.
3. A task counts as finished work only when Status = Done. The Workload sheet updates automatically.
4. If you swap a task with someone, change the Owner cell and tell the team. Totals recalculate.
5. To sort by ID low to high: click the filter arrow on the ID header and choose Sort Smallest to Largest (IDs are plain numbers 1, 2, 3... in section order). Sort by Owner, Status or Target date the same way.
6. Section 15 (Extras) are tasks added on top of the project document's requirements.
7. To share online: upload this file to Google Drive, open it with Google Sheets, then Share with the team (Editor).

## Tasks
ID | Section | Task | Weight | Owner | Depends on | Target date | Status | Notes
1 | 0. Proposal | Pick the game idea (everyone proposes, leader decides) | 2 | Mohamed |  | 2026-11-08 | Not started
2 | 0. Proposal | Write game name + description paragraph (how it is played, goal) | 2 | Nour | 1 | 2026-11-20 | Not started
3 | 0. Proposal | Make the example image for the proposal | 1 | Rahma | 1 | 2026-11-20 | Not started
4 | 0. Proposal | Add member names, IDs and team number | 1 | Mohamed |  | 2026-11-26 | Not started
5 | 0. Proposal | Submit proposal on Moodle (leader only) | 1 | Mohamed | 2, 3, 4 | 2026-11-28 | Not started
6 | 1. Project setup | Restructure folders (engine/, assets/) | 2 | Mohamed |  | 2026-11-03 | Not started
7 | 1. Project setup | Update CMakeLists.txt (new sources, copy assets next to the exe) | 2 | Mohamed | 6 | 2026-11-03 | Not started
8 | 1. Project setup | Add JSON parser (nlohmann/json) | 1 | Mohamed |  | 2026-11-03 | Not started
9 | 1. Project setup | Add stb_image | 1 | Hesham |  | 2026-11-03 | Not started
10 | 1. Project setup | Add tinyobjloader and GLM | 1 | Hesham |  | 2026-11-03 | Not started
11 | 1. Project setup | Decide what to do with the Phase 1 shapes | 1 | Mohamed |  | 2026-11-03 | Not started
12 | 1. Project setup | Update .gitignore and commit the project PDF | 1 | Mohamed |  | 2026-11-03 | Not started
13 | 1. Project setup | Agree on a branch strategy | 1 | Mohamed |  | 2026-11-03 | Not started
14 | 2. Core ECS | Component abstract base class | 2 | Mohamed | 6 | 2026-11-10 | Not started
15 | 2. Core ECS | Entity class (name, parent, local transform, components) | 3 | Mohamed | 14 | 2026-11-10 | Not started
16 | 2. Core ECS | Entity methods: addComponent, getComponent, getLocalToWorldMatrix | 3 | Mohamed | 15 | 2026-11-10 | Not started
17 | 2. Core ECS | World class (add, delete, lookup) | 2 | Mohamed | 15 | 2026-11-10 | Not started
18 | 2. Core ECS | Component factory/registry by type name | 3 | Mohamed | 14 | 2026-11-10 | Not started
19 | 2. Core ECS | Deferred entity deletion | 2 | Mohamed | 17 | 2026-11-10 | Not started
20 | 3. Assets | ShaderProgram wrapper (uniform setters + location cache) | 3 | Nour | 7 | 2026-11-14 | Not started
21 | 3. Assets | Texture2D loader (stb_image, mipmaps) | 3 | Nour | 9 | 2026-11-14 | Not started
22 | 3. Assets | Sampler (filtering, wrapping, anisotropy) | 2 | Nour |  | 2026-11-14 | Not started
23 | 3. Assets | Mesh (VBO, EBO, VAO, attributes) | 4 | Nour |  | 2026-11-14 | Not started
24 | 3. Assets | OBJ model loading | 3 | Nour | 23, 10 | 2026-11-14 | Not started
25 | 3. Assets | Mesh deserialization from the scene file | 2 | Nour | 23, 24 | 2026-11-14 | Not started
26 | 3. Assets | Deserialization functions for all assets | 3 | Nour | 20-23 | 2026-11-14 | Not started
27 | 3. Assets | AssetLoader<T> template singleton (name -> asset map) | 3 | Nour |  | 2026-11-14 | Not started
28 | 3. Assets | Free GPU resources on exit / scene change | 2 | Nour | 27 | 2026-11-17 | Not started
29 | 4. Pipeline state & materials | PipelineState struct (culling, depth, blending, color/depth masks) | 3 | Rahma |  | 2026-11-14 | Not started
30 | 4. Pipeline state & materials | PipelineState::setup() applies state to OpenGL | 3 | Rahma | 29 | 2026-11-14 | Not started
31 | 4. Pipeline state & materials | PipelineState deserialization | 3 | Rahma | 29 | 2026-11-14 | Not started
32 | 4. Pipeline state & materials | Material abstract base class | 2 | Rahma | 30 | 2026-11-14 | Not started
33 | 4. Pipeline state & materials | TintedMaterial | 2 | Rahma | 32, 20 | 2026-11-14 | Not started
34 | 4. Pipeline state & materials | TexturedMaterial | 3 | Rahma | 32, 21, 22 | 2026-11-14 | Not started
35 | 4. Pipeline state & materials | Material asset loader with factory by type name | 3 | Rahma | 27, 33, 34 | 2026-11-17 | Not started
36 | 5. Components | MeshRendererComponent | 3 | Hesham | 14, 23, 32 | 2026-11-14 | Not started
37 | 5. Components | CameraComponent (type, FOV, ortho height, near/far) | 3 | Hesham | 14 | 2026-11-14 | Not started
38 | 5. Components | Camera view / projection / view-projection matrices | 3 | Hesham | 37 | 2026-11-14 | Not started
39 | 5. Components | FreeCameraControllerComponent (parameters) | 4 | Hesham | 37 | 2026-11-14 | Not started
40 | 5. Components | Optional helper components (rotation / movement) | 2 | Hesham | 14 | 2026-11-17 | Not started
41 | 6. Forward renderer | Loop entities, find camera and drawables | 3 | Rahma | 36, 37, 17 | 2026-11-20 | Not started
42 | 6. Forward renderer | Compute distance from the camera | 1 | Rahma | 41 | 2026-11-20 | Not started
43 | 6. Forward renderer | Split into opaque and transparent lists | 2 | Rahma | 32, 41 | 2026-11-20 | Not started
44 | 6. Forward renderer | Sort the opaque list | 1 | Rahma | 43 | 2026-11-20 | Not started
45 | 6. Forward renderer | Draw order: opaque, sky, transparent far-to-near | 4 | Rahma | 43, 51 | 2026-11-20 | Not started
46 | 6. Forward renderer | Per-object draw (material setup, MVP uniform, draw mesh) | 3 | Rahma | 41 | 2026-11-20 | Not started
47 | 6. Forward renderer | Handle missing camera and window resize | 2 | Rahma | 41 | 2026-11-20 | Not started
48 | 6. Forward renderer | Correct clears (color, depth, depth mask) | 2 | Rahma | 41 | 2026-11-20 | Not started
49 | 7. Sky | Sky sphere/cube mesh + sky texture | 3 | Nour | 21, 23 | 2026-11-20 | Not started
50 | 7. Sky | Sky shader (follows camera position) | 3 | Nour | 20 | 2026-11-20 | Not started
51 | 7. Sky | Draw at far plane (depth trick) | 3 | Nour | 50 | 2026-11-20 | Not started
52 | 7. Sky | Sky pipeline state | 2 | Nour | 29 | 2026-11-20 | Not started
53 | 8. Post-processing | Framebuffer (color + depth attachments) | 4 | Hesham |  | 2026-11-24 | Not started
54 | 8. Post-processing | Render the scene into the framebuffer | 2 | Hesham | 53, 45 | 2026-11-24 | Not started
55 | 8. Post-processing | Fullscreen triangle | 2 | Hesham |  | 2026-11-24 | Not started
56 | 8. Post-processing | Post-process shader(s) | 3 | Hesham | 55 | 2026-11-24 | Not started
57 | 8. Post-processing | Scene-configurable effects (optional chaining) | 3 | Hesham | 56, 69 | 2026-11-24 | Not started
58 | 8. Post-processing | Resize the framebuffer on window resize | 2 | Hesham | 53 | 2026-11-24 | Not started
59 | 9. Free camera system | Mouse look (yaw, pitch, clamp) | 3 | Hesham | 39 | 2026-11-20 | Not started
60 | 9. Free camera system | WASD + Q/E movement relative to camera | 2 | Hesham | 39 | 2026-11-20 | Not started
61 | 9. Free camera system | Shift for speed, scroll for zoom | 1 | Hesham | 60 | 2026-11-20 | Not started
62 | 9. Free camera system | Cursor lock / unlock | 1 | Hesham | 59 | 2026-11-20 | Not started
63 | 10. Application | Window setup, main loop, delta time | 3 | Mohamed | 7 | 2026-11-17 | Not started
64 | 10. Application | Scene loading and switching | 3 | Mohamed | 68 | 2026-11-17 | Not started
65 | 10. Application | Clean shutdown (destroy world and assets) | 2 | Mohamed | 28, 17 | 2026-11-17 | Not started
66 | 11. Scene file & deserialization | Define the JSON scene schema | 3 | Mohamed |  | 2026-11-06 | Not started
67 | 11. Scene file & deserialization | Parse the assets section and load assets | 3 | Mohamed | 66, 27 | 2026-11-17 | Not started
68 | 11. Scene file & deserialization | Parse entities and scene graph (parent resolution) | 4 | Mohamed | 66, 18 | 2026-11-20 | Not started
69 | 11. Scene file & deserialization | Configure renderer from the file (sky, post-process) | 2 | Mohamed | Section 6, Section 7, Section 8 | 2026-11-24 | Not started
70 | 11. Scene file & deserialization | Scene path from command line / config | 1 | Nour | 64 | 2026-11-20 | Not started
71 | 11. Scene file & deserialization | Clear error messages (missing asset, bad JSON, unknown component) | 2 | Nour | 67, 68 | 2026-11-24 | Not started
72 | 12. Test scenes | Basic scene: tinted and textured objects | 2 | Hesham | 68 | 2026-11-30 | Not started
73 | 12. Test scenes | Hierarchy scene (parent moves, children follow) | 2 | Hesham | 68 | 2026-11-30 | Not started
74 | 12. Test scenes | Transparency scene (blended objects) | 2 | Rahma | 45 | 2026-11-30 | Not started
75 | 12. Test scenes | Sky + post-process scene | 2 | Hesham | Section 7, Section 8 | 2026-11-30 | Not started
76 | 12. Test scenes | Demo: change a scene by editing JSON only | 1 | Hesham | 72 | 2026-11-30 | Not started
77 | 12. Test scenes | Gather textures and models | 2 | Rahma |  | 2026-11-10 | Not started
78 | 13. Testing & cleanup | Test all pipeline state options | 3 | Rahma | 30, Section 12 | 2026-12-02 | Not started
79 | 13. Testing & cleanup | Test transparent sorting with overlapping objects | 2 | Rahma | 74 | 2026-12-02 | Not started
80 | 13. Testing & cleanup | Test window resize / aspect ratio | 1 | Hesham | 47, 58 | 2026-12-02 | Not started
81 | 13. Testing & cleanup | Test perspective and orthographic cameras | 1 | Hesham | 38 | 2026-12-02 | Not started
82 | 13. Testing & cleanup | OpenGL debug callback and error checks | 2 | Nour | 63 | 2026-11-14 | Not started
83 | 13. Testing & cleanup | Check for leaks (CPU and GPU) | 2 | Nour | 28 | 2026-12-02 | Not started
84 | 13. Testing & cleanup | Verify a clean clone builds (CMake, vendor libs, asset paths) | 2 | Nour |  | 2026-12-03 | Not started
85 | 14. Documentation & delivery | Comment your own code clearly (Mohamed) | 1 | Mohamed |  | 2026-12-03 | Not started
86 | 14. Documentation & delivery | Comment your own code clearly (Nour) | 1 | Nour |  | 2026-12-03 | Not started
87 | 14. Documentation & delivery | Comment your own code clearly (Rahma) | 1 | Rahma |  | 2026-12-03 | Not started
88 | 14. Documentation & delivery | Comment your own code clearly (Hesham) | 1 | Hesham |  | 2026-12-03 | Not started
89 | 14. Documentation & delivery | README: architecture, scene format, controls, build | 2 | Nour |  | 2026-12-03 | Not started
90 | 14. Documentation & delivery | Study the whole pipeline for the discussion (Nour) | 1 | Nour |  | 2026-12-04 | Not started
91 | 14. Documentation & delivery | Study the whole pipeline for the discussion (Rahma) | 1 | Rahma |  | 2026-12-04 | Not started
92 | 14. Documentation & delivery | Study the whole pipeline for the discussion (Hesham) | 1 | Hesham |  | 2026-12-04 | Not started
93 | 14. Documentation & delivery | Remove build files and executables (out/, .vs/, exe) | 1 | Mohamed |  | 2026-12-04 | Not started
94 | 14. Documentation & delivery | Zip and submit on Moodle (leader only) | 1 | Mohamed | 93 | 2026-12-04 | Not started
95 | 14. Documentation & delivery | Prepare the discussion demo (2-3 scenes, who explains what) | 3 | Mohamed |  | 2026-12-05 | Not started
96 | 15. Extras (added) | Kickoff: agree on the interfaces (Component, AssetLoader, Material, Mesh headers) before coding | 2 | Mohamed |  | 2026-11-01 | Not started
97 | 15. Extras (added) | Fix asset paths: copy assets post-build so the exe works from any working directory | 2 | Nour | 7 | 2026-11-08 | Not started
98 | 15. Extras (added) | Git conventions + add teammates as GitHub collaborators (commit under your own name) | 1 | Mohamed |  | 2026-11-01 | Not started
99 | 15. Extras (added) | Weekly integration build + merge check | 2 | Rahma |  | 2026-12-02 | Not started
100 | 15. Extras (added) | Transform math: rotation representation, parent-chain correctness test | 2 | Rahma | 16 | 2026-11-12 | Not started
101 | 15. Extras (added) | Phase 3 readiness: vertex normals/tangents and an extensible material/uniform interface | 2 | Hesham | 23, 32 | 2026-11-14 | Not started

## Workload
Workload per member
Member | Total points | Share | Tasks | Done points | Done % | Remaining points | Core points (sections 0-14) | Extra points (section 15)
Mohamed | 56 | 26.05% | 28 | 0 | 0% | 56 | 53 | 3
Nour | 53 | 24.65% | 23 | 0 | 0% | 53 | 51 | 2
Rahma | 53 | 24.65% | 24 | 0 | 0% | 53 | 49 | 4
Hesham | 53 | 24.65% | 26 | 0 | 0% | 53 | 51 | 2
Team | 215 | 100% | 101 | 0 | 0% | 215 | 204 | 11
Points per section and member
Section | Mohamed | Nour | Rahma | Hesham | Section total
0. Proposal | 4 | 2 | 1 | 0 | 7
1. Project setup | 8 | 0 | 0 | 2 | 10
2. Core ECS | 15 | 0 | 0 | 0 | 15
3. Assets | 0 | 25 | 0 | 0 | 25
4. Pipeline state & materials | 0 | 0 | 19 | 0 | 19
5. Components | 0 | 0 | 0 | 15 | 15
6. Forward renderer | 0 | 0 | 18 | 0 | 18
7. Sky | 0 | 11 | 0 | 0 | 11
8. Post-processing | 0 | 0 | 0 | 16 | 16
9. Free camera system | 0 | 0 | 0 | 7 | 7
10. Application | 8 | 0 | 0 | 0 | 8
11. Scene file & deserialization | 12 | 3 | 0 | 0 | 15
12. Test scenes | 0 | 0 | 4 | 7 | 11
13. Testing & cleanup | 0 | 6 | 5 | 2 | 13
14. Documentation & delivery | 6 | 4 | 2 | 2 | 14
15. Extras (added) | 3 | 2 | 4 | 2 | 11
Total | 56 | 53 | 53 | 53 | 215

## Milestones
Date | Milestone | Who
2026-11-01 | Kickoff done: interfaces agreed, collaborators added | Mohamed
2026-11-03 | Project restructured, libraries added, CMake builds | Mohamed, Hesham
2026-11-10 | ECS core compiles; assets and models gathered | Mohamed, Rahma
2026-11-14 | Assets, materials, pipeline state and components code-complete | Nour, Rahma, Hesham
2026-11-20 | Forward renderer + sky + scene loading draw a scene from JSON | Rahma, Nour, Mohamed
2026-11-24 | Post-processing and scene-configured renderer working | Hesham, Mohamed
2026-11-28 | Proposal submitted on Moodle | Mohamed
2026-11-30 | All test scenes working | Hesham, Rahma
2026-12-02 | Testing finished, bugs fixed | Everyone
2026-12-03 | Code freeze: comments, README, clean-clone build | Everyone
2026-12-04 | Zip and submit (one-day buffer) | Mohamed
2026-12-05 | Phase 2 deadline 23:59 | Mohamed
2026-12-06 | Phase 2 discussion 16:00 | Everyone